## CHECKLIST-TIMELINE CSB
(Agency) PROCUREMENT PLAN FOR (Contract Title)
27 STEPS / CHECKLIST & TIMELINE FOR COMPETITIVE SEALED BIDDING (CSB) PROCUREMENTS
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK)
PLANNING (8 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
1 | Initial Planning Meeting: Identify what you want to procure.
2 | Specification Drafting: Prepare specifications and determine the means for advertising and distributing the solicitation. Develop a direct solicitation list. Hold PRG, determine SBR designation, set MBE and VSBE goals and MBE subgoals, as appropriate. Work with AAG as needed.
3 | Review Green Purchasing Checklist, located on the OSP website. Determine if applicable, complete and submit as required.
4 | Submit specifications to DHS to determine if a Hiring Agreement is applicable for the contract.
5 | Verify if there are Non-Visual Access requirements for the contract and update Section 4.33 in the RFP as needed.
6 | Consult with DBM for certification of Services contract procurements in accordance with the State Policy in State Personnel & Pension (SPP) §13-402 as defined in SPP §13-401 and SFP §11-101.
7 | Obtain internal agency approvals. (Program, AAG, etc.)
8 | Submit and Obtain approval of specifications from DGS OSP.
PROCURING (18 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
9 | IFB Publication: Advertise (post) the availability of the solicitation in eMaryland Marketplace Advantage (eMMA) and elsewhere. DIRECT SOLICIT: Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues.
10 | Hold a Pre-Bid Conference.
11 | Prepare and distribute Minutes or a Summary of the conference to all known potential bidders and post in eMMA.
12 | Receive and consider solicitation questions; distribute answers to questions to all known potential bidders and post in eMMA.
13 | Prepare an addendum for any changes to the solicitation; distribute to all known potential bidders and post in eMMA.
14 | Bid Due Date: The Procurement Officer receives bids.
15 | Bids are opened publicly and a record is prepared of the bid opening (a bid abstract).
16 | Low bid is checked for compliance.
17 | Decide whether any deficiency in the low bid is waivable, curable, or renders the bid nonresponsive. Confirm low bidder is a responsible bidder. (Consult your AAG and write a Procurement Officer's Determination, if necessary.)
18 | Bidder is notified of any curable deficiencies.
19 | Bidder provides other required additional information or documents.
20 | Award Recommendation: An award recommendation is made. The apparent awardee is informed and appropriate contract documents, affidavits, etc are sent for signature.
21 | If waiver request made, agency requests and considers MBE waiver documentation from recommended awardee, required additional MBE forms are obtained, if necessary, and the contractor signs the contract and affidavits; sends them to the Procurement Officer.
22 | Final internal agency approvals are obtained.
PROCURING (18 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
23 | Contract Approval / BPW Date: The award is submitted for DGS OSP and, if necessary, BPW approval.
24 | The contract is signed by the agency and transmitted to the Contractor.
25 | Make sure the procurement file is completed, including a set of ALL bids received. (See COMAR 21.05.01.06-.07 for Procurement file requirements.)
26 | Post contract award on eMMA within 30 days of contract execution after all approvals have been finalized.
ENTER FMIS ADPICS # HERE:
ENTER eMMA Contract Award Posting # HERE:
PERFORMING (2 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
27 | Work initiation conference is held. (Kick-off Meeting.)
28 | Contract Commencement Date: Contractor commences work.
I confirm that the above steps were completed for this Procurement.
| Procurement Officer Signature |  | Date
| Supervisor Signature |  | Date
Version 3, Dated 2/4/2022

## CHECKLIST-TIMELINE CSP
(Agency) PROCUREMENT PLAN FOR (Contract Title)
41 STEPS / CHECKLIST & TIMELINE FOR COMPETITIVE SEALED PROPOSALS (CSP) PROCUREMENTS
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK)
PLANNING (9 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
1 | Initial Planning Meeting: Identify what you want to procure.
> BPO Number of current contract (final option)
> Expiration Date of current contract (final option)
> Procurement Method
2 | Specification Drafting: Prepare specifications and determine the means for advertising and distributing the solicitation. Develop a direct solicitation list. Hold PRG, determine SBR designation, set MBE and VSBE goals and MBE subgoals, as appropriate. Work with AAG as needed.
3 | Review Green Purchasing Checklist, located on the OSP website. Determine if applicable, complete and submit as required.
4 | Submit specifications to DHS to determine if a Hiring Agreement is applicable for the contract.
5 | Verify if there are Non-Visual Access requirements for the contract and update Section 4.33 in the RFP as needed.
6 | Consult with DBM for certification of Services contract procurements in accordance with the State Policy in State Personnel & Pension (SPP) §13-402 as defined in SPP §13-401 and SFP §11-101.
7 | Confirm members for the Evaluation Committee.
8 | Obtain internal agency approvals. (Program, AAG, etc.)
9 | Submit and Obtain approval of specifications from DGS OSP.
PROCURING (31 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
10 | RFP Publication: Advertise (post) the availability of the solicitation in eMaryland MarketPlace and elsewhere. DIRECT SOLICIT: Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues.
11 | Hold a Pre-Proposal Conference.
12 | Prepare and distribute Minutes or a Summary of the conference to all known potential offerors and post in eMMA.
13 | Receive and consider solicitation questions; distribute answers to questions to all known potential offerors and post in eMMA.
14 | Prepare an addendum for any changes to the solicitation; distribute to all known potential offerors and post in eMMA.
15 | Proposal Due Date: The Procurement Officer receives proposals.
16 | Technical proposals are opened in the presence of at least 2 State employees, not publicly, a record is prepared of the proposals received (a register of proposals) and of the opening. Check for separate technical and financial proposals, bond or other required security. Do not open financial proposals.
17 | Evaluation Period Begins: Technical Proposals are checked for compliance with various requirements, checking first the completion of MBE forms. (Any MBE deficiencies should be confirmed with AAG to see if curable, waivable, or fatal.)
PROCURING (31 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
18 | Evaluation Kick-off Meeting: The Procurement Officer reviews the evaluation committee member requirements to the evaluation committee by providing them a copy of the guidelines and has them sign the confidentiality and commitment document, then distributes the technical proposals to each member to individually read.
19 | The evaluation committee meets to discuss the technical proposals, including strengths and weaknesses, ambiguities, and omissions .
20 | “Cure letters” are issued to Offerors to address:
> Omitted items or information and exceptions
> Written clarifications of ambiguous material
> Written explanations or justifications for any information that is not sufficiently supported
21 | Cure letter responses are received and reviewed.
22 | The evaluation committee prepares generic and specific questions to ask offerors at the oral presentations, including any lingering or new questions based upon the cure letter responses.
23 | Oral presentations are held with all offerors.
24 | Offerors submit additional information, clarifications or changes based upon the oral presentations
25 | If any Offeror is determined to be not technically qualified or not reasonably susceptible of being selected for award, a Procurement Officer's Determination must be written and the Offeror must be rejected, prior to opening of Financial proposals.
26 | Final Technical Evaluation Meeting: The evaluation committee makes final technically qualified determinations for proposals and ranks the remaining technically qualified proposals based upon the evaluation criteria in the RFP, including proposals, cures & orals.
27 | Opening of Financial Proposals: Open and review financials for offerors with technically qualified proposals.
28 | If necessary, discussions are held concerning the financial proposals with ALL Offerors still being considered.
29 | Best and Final Offers (BAFO) are invited, received and evaluated.
30 | Final Financial and Overall Ranking Meeting: Based upon the combined technical and financial rankings the evaluation committee recommends an offeror to receive the contract award.
31 | Award Recommendation Date: The procurement officer and agency head accept the recommendation of the evaluation committee or select a different offeror for the award.
32 | The apparent awardee is informed and appropriate contract documents, affidavits, etc are sent for signature.
33 | The contractor signs the contract and provides all required post award items, such as:
> 2 additional MBE forms, or waiver justification
> Bonds
> Insurance
> Contract and Conflict-of-Interest Affidavits
PROCURING (31 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
34 | Non-winning offerors are notified of their status and provided all permissible information
35 | Debriefings are scheduled and held.
36 | Final internal agency approvals are obtained.
37 | Contract Approval / BPW Date: The award is submitted for DGS OSP and, if necessary, BPW approval.
38 | The contract is signed by the agency and transmitted to the Contractor.
39 | Make sure the procurement file is completed. Excess copies of proposals are destroyed and the procurement file is completed. (One full set of all Offerors' proposals - technical, financial & BAFO - must be maintained in the file. See COMAR 21.05.01.06-.07 for Procurement file requirements.)
40 | Post contract award on eMMA within 30 days of contract execution after all approvals have been finalized.
ENTER FMIS ADPICS # HERE:
ENTER eMMA Contract Award Posting # HERE:
PERFORMING (2 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
41 | Work initiation conference is held. (Kick-off Meeting.)
42 | Contract Commencement Date: Contractor commences work.
I confirm that the above steps were completed for this Procurement.
| Procurement Officer Signature |  | Date
| Supervisor Signature |  | Date
Version 4, Dated 10/12/2023

## TIMEFRAMES
24 STEPS FOR PROCUREMENTS SUBJECT TO DGS OSP APPROVAL |  |  | PROCUREMENT STEPS AND MINIMUM TIME FRAMES FOR COMPLETION | [8 empty] | PROCUREMENT STEPS AND MINIMUM TIME FRAMES FOR COMPLETION
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK) |  |  | (Except for the first 7 STEPS) | [8 empty] | (Except for the first 8 STEPS)
| PLANNING (4 steps) |  | Competitve Sealed Bidding | No DGS OSP Approval with No MBE goal | No DGS OSP Approval with MBE goal | No DGS OSP Approval with No MBE goal | No DGS OSP Approval with MBE goal | DGS OSP Approval with No MBE goal | DGS OSP Approval with MBE goal | DGS OSP Approval with No MBE goal | DGS OSP Approval with MBE goal | Competitve Sealed Proposals | No DGS OSP Approval with No MBE goal | No DGS OSP Approval with MBE goal | No DGS OSP Approval with No MBE goal | No DGS OSP Approval with MBE goal | DGS OSP Approval with No MBE goal | DGS OSP Approval with MBE goal | DGS OSP Approval with No MBE goal | DGS OSP Approval with MBE goal
1 | Identify what you want to procure. |  |  | <$200,001 | <$200,001 | >$200,000 | >$200,000 | <$200,001 | <$200,001 | >$200,000 | >$200,000 |  | <$200,001 | <$200,001 | >$200,000 | >$200,000 | <$200,001 | <$200,001 | >$200,000 | >$200,000
2 | Prepare specifications and determine the means for advertising and distributing the solicitation.
3 | Obtain internal agency approvals.
4 | Obtain approval of specifications from DGS OSP.
|  |  | (DGS OSP Approval) |  |  |  |  | 28-35 days | 28-35 days | 28-35 days | 28-35 days | (DGS OSP Approval) |  |  |  |  | 28-35 days | 28-35 days | 28-45 days | 28-45 days
PROCURING (18 steps)
5 | Advertise (post) the availability of the solicitation in eMarylandMarketPlace and elsewhere. |  | (Advertise & Receive Bids) | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | (Advertise & Receive Proposals) | 30-40 days | 30-40 days | 30-60 days | 30-60 days | 30-40 days | 30-40 days | 30-60 days | 30-60 days
6 | Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues.
7 | Hold a Pre-Bid/Proposal Conference.
8 | Prepare and distribute Minutes or a Summary of the conference to ALL known potential bidders/offerors.
9 | Solicitation questions are received and answered, with answers to substantive questions being distributed to ALL known potential bidders/offerors.
10 | Any changes to the solicitation are prepared in an addendum and distributed to ALL known potential bidders/offerors. |  | (Determine Responsiveness) | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | (Determine if Proposals | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days
11 | The Procurement Officer receives bids/proposals. | [10 empty] | are Reasonably Susceptible of
12 | Bids/proposals are opened. * | [10 empty] | Receiving an Award) *
| » | Bids are opened publicly and a record is prepared of the bid opening (a bid abstract). | (Determine Responsibility) | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | (Notification & Debriefings) | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days
| » | Proposals are opened in the presence of at least 2 State employees, not publicly, and a record is prepared of the proposals received (a register of proposals) and of the opening.
13 | Bids/proposals are checked for compliance with various requirements, checking first the completion of MBE forms. |  | (Notice of Award) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | (Notice of Award) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE)
14 | A decision is made of whether any deficiency is waivable, versus curable, versus fatal. * |  | (Receive final MBE forms) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) | (Receive final MBE forms) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days)
15 | Vendors are notified of curable deficiencies. ** |  | (Outside Agency Approvals) |  |  | 30 days - BPW * | 30 days - BPW * | 7-14 days - DGS OSP | 7-14 days - DGS OSP | 44 days | 44 days | (Outside Agency Approvals) |  |  | 30 days - BPW ** | 30 days - BPW ** | 7-14 days - DGS OSP | 7-14 days - DGS OSP | 44 days | 44 days
16 | Required additional information or documents are received and evaluated. ** |  | (Execute signed Contract) | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | (Execute signed Contract) | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days
17 | An award decision is made. **
18 | Required additional MBE forms are obtained, if necessary, and the contractor signs the contract. ** |  | SUBTOTAL to CONTRACT AWARD | 23-53 days | 36-62 days | 51-81 days | 64-90 days | 58-98 days | 71-107 days | 95-132 days | 108-141 days | SUBTOTAL to CONTRACT AWARD | 73-129 days | 86-138 days | 101-177 days | 114-186 days | 108-174 days | 121-183 days | 145-238 days | 158-247 days
19 | Final internal agency approvals are obtained. |  | (Core Procurement Phase) | [8 empty] | (Core Procurement Phase)
20 | The award is submitted for DGS OSP and, if necessary, BPW approval.
21 | The contract is signed by the agency and transmitted to the Contractor. |  | COMMENCEMENT of CONTRACT/ DELIVERY DATE | 1-7 days | 1-7 days | 7-14 days | 7-14 days | 1-7 days | 1-7 days | 7-14 days | 7-14 days | COMMENCEMENT of CONTRACT | 7-14 days | 7-14 days | 14-30 days | 14-30 days | 7-14 days | 7-14 days | 14-30 days | 14-30 days
22 | Excess bids/proposals are destroyed and the procurement file is completed.
| PERFORMING (2 steps) |  | TOTAL | 24-60 days | 37-69 days | 58-95 days | 71-104 days | 59-105 days | 72-114 days | 102-146 days | 115-155 days | TOTAL | 80-143 days | 93-152 days | 115-207 days | 128-216 days | 115-188 days | 128-197 days | 159-258 days | 172-277 days
23 | Work initiation conference is held.
24 | Contractor commences work. |  | * Only includes lead time for formal item submission to the BPW. Does not include any time for internal agency approvals. | [8 empty] | * Cumulative timeframe for 6 STEPS.
| * Steps are the same for CSB and CSP with minor variances. | [10 empty] | ** Only includes lead time for formal item submission to the BPW. Does not include any time for internal agency approvals.
** Steps have variances between CSB and CSP, and CSP has additional steps added in between these steps.
CSP -
Steps 1-14 are the same as CSB.
15 | The evaluation committee members individually read the technical proposals
16 | The evaluation committee meets to discuss the proposals, including strengths and weaknesses, ambiguities, and omissions
17 | “Cure letters” are issued to obtain:
—Omitted items or information
—But, missing/incomplete MBE forms generally are not curable
—Written clarifications of ambiguous material
—Written explanations or justifications for any information that is not sufficiently supported
(Vendors are notified of curable deficiencies - Issues of responsibility for sealed bid procurements, #15)
18 | The evaluation committee prepares generic and specific questions to ask offerors at the oral presentations, including any lingering or new questions based upon the cure letter responses
(Required additional information or documents is received and evaluated, #16)
19 | Oral presentations are held with offerors
20 | Offerors submit additional information, clarifications or changes based upon the oral presentations
21 | The evaluation committee makes final technically qualified determinations for proposals and ranks the remaining technically qualified proposals based upon the evaluation criteria in the RFP
22 | Financial proposals are opened and reviewed for offerors with technically qualified proposals
23 | If necessary, discussions are held concerning the financial proposals
24 | Best and Final Offers (BAFO) are invited, received and evaluated
25 | Based upon the combined technical and financial rankings the evaluation committee recommends an offeror to receive the contract award
26 | The procurement officer and agency head accept the recommendation of the evaluation committee or select a different offeror for the award
(An award decision is made, #17)
27 | The contractor signs the contract and provides all required post award items, such as:
—2 additional MBE forms, or waiver justification
—Bonds
—Insurance
—Contract and Conflict-of-Interest Affidavits
(Required additional MBE forms are obtained and the contractor signs the contract, #18)
28 | Non-winning offerors are notified of their status and provided all permissible information
29 | Debriefings are held
Picks up with #19 from CSB and is the same until the end for a total of 35 Steps for CSPs.