## INSTRUCTIONS
Instructions for Using Procurement Timeline
1. Procurement Officer (PO) determines which timeline template to use (IFB, Sole Source, RFP, etc.)
2. PO enters DATE they received ALL REQUIRED documents into COLUMN D. The spreadsheet will automatically calculate the expected timeline in Row 6 and the actual timeline in row 7. If the actual date a step is completed varies from the expected date, PO should update that cell in row 7 and the spreadsheet will automatically calculate the remainind dates.
3. If BPW is not required, use AGENCY AWARD date as the final expected date.
4. Please remember if you deviate from the prescribed time, provide comments to show the reason for deviation.
5. Points to consider for all procurement methods during the PLANNING PHASE include but are not limited to:
*Information Technology Requests (doit.intake@maryland.gov)
*Green Purchasing (dgs.buygreen@maryland.gov)
*Hiring Agreement Determination (Kenneth Jessup DHS - hiring.agreements@maryland.gov)
*Non-Visual Access (NVA) Compliance Check (nva.info@maryland.gov)
*DBM Services Contracts SFP §11-101 Compliance Check (Joan Peacock - joan.peacock@maryland.gov)
*Procurement Review Group - (dgs.osp-prg@maryland.gov)
6. Points to consider :
Direct Solicit to known firms, MBEs/VSBEs/small businesses (or new term CSBs) for all methods as practical.
DGS OSP Procurement Timeline and Milestone Tool - v1 01.21.2025

## IFB
INVITATION FOR BIDS (IFB) |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | PROCUREMENT PHASE | [5 empty] | EVALUATION & AWARD | [6 empty] | AWARD APPROVAL |  | Total Time
|  | Step No. | Submission to OSP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | Agency Delegated Award | BPW | Total Time (Days)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 2 DAYS | 7 DAYS | 5 DAYS | 7 DAYS | 30 DAYS from advertisement | 1 DAY | 5 DAYS | 1 DAY | 10 DAYS | 3 DAYS | 10 DAYS | 7 DAYS | 10 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | SOLICITATION POSTED TO EMMA | PRE-BID CONFERENCE (SITE VISITS IF NECESSARY) | QUESTIONS DUE | ADDENDA ISSUED | BIDS DUE | BID OPENING | BID REVIEW, INCLUDING MBE FORMS, ETC. | INTENT TO AWARD LETTERS (REQUEST MBE DOCS, ETC.) | RECEIVE PACKAGE FROM VENDOR & PROTEST WAITING PERIOD | REVIEW RETURNED PACKAGE | LEGAL REVIEW | AWARD RECOMMENDATION | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
Elevator Maint | Sample | Example | 2024-03-25 | 2024-03-26 | 2024-03-29 | 2024-03-31 | 2024-04-02 | 2024-04-02 | 2024-04-04 | 2024-04-11 | 2024-04-16 | 2024-04-23 | 2024-05-04 | 2024-05-05 | 2024-05-10 | 2024-05-11 | 2024-05-21 | 2024-05-24 | 2024-06-03 | 2024-06-10 | 2024-06-20 | 2024-07-25 | 69
| Expected |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-08 | 2025-02-15 | 2025-02-26 | 2025-02-27 | 2025-03-04 | 2025-03-05 | 2025-03-15 | 2025-03-18 | 2025-03-28 | 2025-04-04 | 2025-04-14 | 2025-05-19 | 69
| Actual |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-20 | 2025-01-20 | 2025-01-22 | 2025-01-31 | 2025-02-05 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-02-28 | 2025-03-10 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-09 | 2025-05-14 | 69
Comments/Notes
Formulas:
AWARD APPROVAL = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+10)
IF BPW APPROVAL IS NEEDED = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+45)
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]

## RFP
Request for Proposals (RFP) |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | PROCUREMENT PHASE | [6 empty] | EVALUATION & AWARD | [21 empty] | AWARD PHASE |  | Total Time
|  | Step No. | Submission to OSP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | Agency Award | BPW | No. of Days (Does not include AWARD PHASE)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 2 DAYS | 7 DAYS | 7 DAYS | 7 DAYS | 7 DAYS before Step 13 | 30 DAYS after Step 6 | 2 DAYS | 14 DAYS | 5 DAYS | 4 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 5 DAYS | 2 DAYS | 2 DAYS | 4 DAYS | 7 DAYS | 7 DAYS | 2 DAYS | 2 DAYS | 3 DAYS | 2 DAYS | 5 DAYS | 2 DAYS | 4 DAYS | 7 DAYS | 7 DAYS | 5 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | SOLICITATION POSTED TO EMMA | PRE-PROPOSAL CONFERENCE (SITE VISITS IF NECESSARY) | QUESTIONS DUE | ADDENDA ISSUED | TECH EVAL COMMITTEE KICKOFF MEETING | TECHNICAL PROPOSALS DUE | TECHNICAL PROPOSALS OPENING/ DISTRIBUTION | TECHNICAL EVALUATION COMMITTEE MEETING, INCLUDING MBE FORMS REVIEW, ETC. | ORAL PRESENTATIONS/COMMITTEE MEETING TO REVIEW ORALS | SEND CURE NOTICE TO OFFEROR IF APPLICABLE | RECEIVE OFFEROR RESPONSE | FINAL TECHNICAL EVALUATION COMMITTEE MEETING | NON SELECT LETTER DRAFT | LEGAL REVIEW | SEND NON-SELECT LETTER TO OFFEROR | REQUEST FINANCIAL PROPOSAL | DEBRIEFS TO OFFERORS | WAIT 7 DAYS (PROTEST WAITING PERIOD) | FINANCIAL PROPOSAL DUE | FINANCIAL PROPOSAL OPENING | REQUEST BAFO | RECEIVE BAFO RESPONSE | FINAL FINANCIAL AND OVERALL RANKING(S) | LEGAL REVIEW | SEND NON-SELECT & INTENT TO AWARD/SELECT LETTERS (REQUEST MBE DOCS, ETC.) | DEBRIEFS TO OFFERORS | WAIT 7 DAYS (PROTEST WAITING PERIOD) | AWARD RECOMMENDATION | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
Reverse Auction RITMO197560 | Sample | Example | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-05-01 | 2024-05-08 | 2024-05-10 | 2024-05-24 | 2024-05-29 | 2024-06-02 | 2024-06-04 | 2024-06-06 | 2024-06-08 | 2024-06-13 | 2024-06-15 | 2024-06-17 | 2024-06-21 | 2024-06-28 | 2024-06-24 | 2024-06-26 | 2024-06-28 | 2024-07-01 | 2024-07-03 | 2024-07-08 | 2024-07-10 | 2024-07-14 | 2024-07-21 | 2024-07-28 | 2024-08-02 | 2024-09-11 | 120
| Expected |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-26 | 2025-03-05 | 2025-03-07 | 2025-03-21 | 2025-03-26 | 2025-03-30 | 2025-04-01 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-25 | 2025-04-21 | 2025-04-23 | 2025-04-25 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-07 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-07-09 | 120
| Actual |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-26 | 2025-03-05 | 2025-03-07 | 2025-03-21 | 2025-03-26 | 2025-03-30 | 2025-04-01 | 2025-04-03 | 2025-04-05 | 2025-04-10 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-25 | 2025-04-21 | 2025-04-23 | 2025-04-25 | 2025-04-28 | 2025-04-30 | 2025-05-05 | 2025-05-07 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-05-30 | 2025-07-09 | 120
Comments/Notes
Formulas:
AWARD PHASE = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+5)
IF BPW APPROVAL IS NEEDED = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+45)
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]

## TORFP
Task Order RFP (TORFP) For IT Purchases, etc. |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | PROCUREMENT PHASE | [6 empty] | EVALUATION & AWARD | [21 empty] | AWARD PHASE |  | Total Time
|  | Step No. | Submission to OSP | 1 1 DAY | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | Agency Award | BPW | No. of Days (Does not include AWARD PHASE)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 2 DAYS | 7 DAYS | 5 DAYS | 5 DAYS | 5 DAYS before Step 11 | 7 DAYS after Step 9 | 2 DAYS | 10 DAYS | 5 DAYS | 4 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 5 DAYS | 2 DAYS | 2 DAYS | 4 DAYS | 7 DAYS | 7 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 5 DAYS | 2 DAYS | 4 DAYS | 7 DAYS | 7 DAYS | 5 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | SOLICITATION POSTED TO EMMA | PRE-PROPOSAL CONFERENCE | QUESTIONS DUE | ADDENDA ISSUED | TECH EVAL COMMITTEE KICKOFF MEETING | TECHNICAL PROPOSALS DUE | TECHNICAL PROPOSALS OPENING/ DISTRIBUTION | TECHNICAL EVALUATION COMMITTEE MEETING, INCLUDING MBE FORMS REVIEW, ETC. | ORAL PRESENTATIONS/ COMMITTEE MEETING TO REVIEW ORALS | SEND CURE NOTICE TO OFFEROR IF APPLICABLE | RECEIVE OFFEROR RESPONSE | FINAL TECHNICAL EVALUATION COMMITTEE MEETING | NON SELECT LETTER DRAFT | LEGAL REVIEW | SEND NON-SELECT & INTENT TO AWARD/SELECT LETTER TO OFFEROR (REQUEST MBE DOCS, ETC.) | REQUEST FINANCIAL PROPOSAL | DEBRIEFS TO OFFERORS | WAIT 7 DAYS (PROTEST WAITING PERIOD) | FINANCIAL PROPOSAL DUE | FINANCIAL PROPOSAL OPENING | REQUEST BAFO | RECEIVE BAFO RESPONSE | FINAL FINANCIAL AND OVERALL RANKING(S) | LEGAL REVIEW | SEND NON-SELECT LETTERS | DEBRIEFS TO OFFERORS | WAIT 7 DAYS (PROTEST WAITING PERIOD) | AWARD RECOMMENDATION | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
Reverse Auction RITMO197560 | Sample | Example | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-13 | 2024-04-18 | 2024-04-20 | 2024-04-25 | 2024-04-27 | 2024-05-07 | 2024-05-12 | 2024-05-16 | 2024-05-18 | 2024-05-20 | 2024-05-22 | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-06-02 | 2024-06-09 | 2024-06-05 | 2024-06-07 | 2024-06-09 | 2024-06-11 | 2024-06-13 | 2024-06-18 | 2024-06-20 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-13 | 2024-08-22 | 100
| Expected |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-22 | 2025-03-04 | 2025-03-09 | 2025-03-13 | 2025-03-15 | 2025-03-17 | 2025-03-19 | 2025-03-24 | 2025-03-26 | 2025-03-26 | 2025-03-30 | 2025-04-06 | 2025-04-02 | 2025-04-04 | 2025-04-06 | 2025-04-08 | 2025-04-10 | 2025-04-15 | 2025-04-17 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-10 | 2025-06-19 | 100
| Actual |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-08 | 2025-02-13 | 2025-02-15 | 2025-02-20 | 2025-02-22 | 2025-03-04 | 2025-03-09 | 2025-03-13 | 2025-03-15 | 2025-03-17 | 2025-03-19 | 2025-03-24 | 2025-03-26 | 2025-03-26 | 2025-03-30 | 2025-04-06 | 2025-04-02 | 2025-04-04 | 2025-04-06 | 2025-04-08 | 2025-04-10 | 2025-04-15 | 2025-04-17 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-10 | 2025-06-19 | 100
Comments/Notes
Formulas:
AWARD PHASE = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+5)
IF BPW APPROVAL IS NEEDED = IF([AWARD RECOMMENDATION]="","",[AWARD RECOMMENDATION]+45)
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]

## PORFP
Purchase Order RFP (PORFP) For IT Commodities (Saas, etc.) |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | PROCUREMENT PHASE | [8 empty] | EVALUATION & AWARD |  |  |  | AWARD APPROVAL |  | Total Time
|  | Step No. | Submission to OSP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | Agency Delegated Award(s) | BPW | No. of Days (Does not include AWARD PHASE)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 2 DAYS | 7 DAYS | 5 DAYS | 7 DAYS | 7 DAYS from addenda |  | 5 DAYS | 1 DAY | 10 DAYS | 3 DAYS | 10 DAYS | 7 DAYS | 10 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | SOLICITATION POSTED TO EMMA | PRE-BID CONFERENCE | QUESTIONS DUE | ADDENDA ISSUED | BIDS DUE | BID OPENING | BID REVIEW, INCLUDING MBE FORMS, ETC. | NOTICE OF INTENT TO AWARD (REQUEST MBE DOCS, ETC.) | RECEIVE PACKAGE FROM VENDOR | REVIEW RETURNED PACKAGE | LEGAL REVIEW | AWARD RECOMMENDATION | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
Laptop Purchase | Sample | Example | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-13 | 2024-04-20 | 2024-04-27 | 2024-04-27 | 2024-05-02 | 2024-05-03 | 2024-05-13 | 2024-05-16 | 2024-05-26 | 2024-06-02 | 2024-06-05 | 2024-07-10 | 50
| Expected |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-02-22 | 2025-02-27 | 2025-02-28 | 2025-03-10 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-02 | 2025-05-07 | 50
| Actual |  | 2025-01-17 | 2025-01-18 | 2025-01-21 | 2025-01-23 | 2025-01-25 | 2025-01-25 | 2025-01-27 | 2025-02-03 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-02-22 | 2025-02-27 | 2025-02-28 | 2025-03-10 | 2025-03-13 | 2025-03-23 | 2025-03-30 | 2025-04-02 | 2025-05-07 | 50
Comments/Notes
Formulas:
AWARD APPROVAL = IF([PROCUREMENT INTAKE]="","",[LEGAL REVIEW]+10)
IF BPW APPROVAL IS NEEDED = IF([PROCUREMENT INTAKE]="","",[LEGAL REVIEW]+45)
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]

## QBS (AE)
Qualification Based Selection (QBS) (A&E) |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | PROCUREMENT PHASE | [8 empty] | EVALUATION & AWARD | [13 empty] | AWARD PHASE |  | Total Time
|  | Step No. | Submission to OSP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | AGENCY AWARD | BPW | No. of Days (Does not include AWARD PHASE)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 2 DAYS | 7 DAY | 5 DAYS | 7 DAYS | 7 DAYS before Step 10 | 30 DAYS | 2 DAYS | 15 DAYS | 7 DAYS | 4 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 2 DAYS | 10 DAYS | 2 DAYS | 0 DAYS | 4 DAYS | 7 DAYS | 7 DAYS | 14 DAYS | 7 DAYS | 5 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | SOLICITATION POSTED TO EMMA | PRE-PROPOSAL CONFERENCE | QUESTIONS DUE | ADDENDA ISSUED | TECH EVAL COMMITTEE KICKOFF MEETING | TECHNICAL PROPOSALS DUE | TECHNICAL PROPOSALS OPENING/ DISTRIBUTION | TECHNICAL EVALUATION COMMITTEE MEETING, INCLUDING MBE FORMS REVIEW, ETC. - includes 10 days for panel to review | ORAL PRESENTATIONS/COMMITTEE MEETING TO REVIEW ORALS | SEND CURE NOTICE TO OFFEROR IF APPLICABLE | RECEIVE OFFEROR CURE RESPONSE | FINAL TECHNICAL EVALUATION COMMITTEE MEETING | FINAL TECHNICAL RANKINGS | NON SELECT LETTER DRAFT | LEGAL REVIEW | SEND NON-SELECT & INTENT TO AWARD/SELECT LETTERS TO OFFEROR (S) (REQUEST MBE DOCS, ETC.) | REQUEST FINANCIAL PROPOSAL | DEBRIEFS TO OFFEROR(S) | WAIT 7 DAYS (PROTEST WAITING PERIOD) | FINANCIAL PROPOSAL DUE | PRICE NEGOTIATIONS | FINAL OVERALL RANKING(S) & AWARD RECOMMENDATION | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
RCI Security Fence Replacement | Sample | Example | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-13 | 2024-04-20 | 2024-04-24 | 2024-05-01 | 2024-05-03 | 2024-05-18 | 2024-05-25 | 2024-05-29 | 2024-05-31 | 2024-06-02 | 2024-06-04 | 2024-06-06 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-29 | 2024-06-25 | 2024-07-09 | 2024-07-16 | 2024-07-21 | 2024-09-04 | 108
| Expected |  | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-13 | 2024-04-20 | 2024-04-24 | 2024-05-01 | 2024-05-03 | 2024-05-18 | 2024-05-25 | 2024-05-29 | 2024-05-31 | 2024-06-02 | 2024-06-04 | 2024-06-06 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-29 | 2024-06-25 | 2024-07-09 | 2024-07-16 | 2024-07-21 | 2024-09-04 | 108
| Actual |  | 2024-03-22 | 2024-03-23 | 2024-03-26 | 2024-03-28 | 2024-03-30 | 2024-03-30 | 2024-04-01 | 2024-04-08 | 2024-04-13 | 2024-04-20 | 2024-04-24 | 2024-05-01 | 2024-05-03 | 2024-05-18 | 2024-05-25 | 2024-05-29 | 2024-05-31 | 2024-06-02 | 2024-06-04 | 2024-06-06 | 2024-06-16 | 2024-06-18 | 2024-06-18 | 2024-06-22 | 2024-06-29 | 2024-06-25 | 2024-07-09 | 2024-07-16 | 2024-07-21 | 2024-09-04 | 108
Comments/Notes
Formulas:
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]

## Sole Source
SOLE SOURCE (SS) |  | PHASE | PROCUREMENT INTAKE |  |  |  |  | AWARD EVALUATION PHASE |  |  |  |  | AWARD PHASE |  | Total Time
|  | Step No. | Submission to OSP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Agency Delegated Award(s) | BPW | No. of Days (Does not include AWARD PHASE)
|  | Days Between Steps |  | 1 DAY | 3 DAYS OSP to review and send comments to end-user if applicable | 2 DAYS end-user to return documents | 2 DAYS |  | 5 DAYS | 7 DAYS | 14 DAYS | 6 DAYS | 10 DAYS | 45 DAYS
|  | Action | START DATE | SEND OSP A FULLY COMPLETED* PROCUREMENT PACKAGE | OSP REVIEWS DOCUMENTS & PROVIDES FEEDBACK TO REQUESTOR | REQUESTOR SUBMITS DOCUMENTS BACK TO OSP | OSP TO APPROVE PROCUREMENT PACKAGE | PROCUREMENT CLOCK STARTS | REVIEW SOLE SOURCE DETERMINATION W/ LEGAL REVIEW | FAIR AND REASONABLE REVIEW | NEGOTIATIONS WITH FIRM (REQUEST MBE FORMS IF APPLICABLE) | AWARD RECOMMENDATION AND/OR POD | IF NO BPW APPROVAL NEEDED, PROCUREMENT FINALIZED | IF BPW APPROVAL IS NEEDED | DAYS OF PROCUREMENT CYCLE
Software Purchase | Sample | Example | 2024-11-01 | 2024-11-22 | 2024-11-25 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-12-02 | 2024-12-09 | 2024-12-23 | 2024-12-29 | 2025-01-08 | 2025-02-22 | 32
| Expected |  | 2025-01-17 | 2025-01-17 | 2025-01-20 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-27 | 2025-02-03 | 2025-02-17 | 2025-02-23 | 2025-03-05 | 2025-04-19 | 32
| Actual |  | 2025-01-17 | 2025-01-17 | 2025-01-20 | 2025-01-22 | 2025-01-22 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-15 | 2025-02-21 | 2025-03-03 | 2025-04-17 | 30
Comments/Notes
Formulas:
AWARD PHASE = IF([PROCUREMENT INTAKE]=0,"",M6+10)
PROCUREMENT INTAKE = [PROCUREMENT INTAKE, row above]