## CSB CHECKLIST
(Agency) PROCUREMENT PROCESS PLAN FOR (Contract Title)
29 STEPS / CHECKLIST & TIMELINE FOR COMPETITIVE SEALED BIDDING (CSB) PROCUREMENTS
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK)
PLANNING (8 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
1 | Initial Planning Meeting: Identify what you want to procure.
2 | Specification Drafting: Prepare specifications and determine the means for advertising and distributing the solicitation. Develop a direct solicitation list. Hold PRG, determine SBR designation, set MBE and VSBE goals and MBE subgoals, as appropriate. Work with AAG as needed. USE CURRENT IFB TEMPLATE.
3 | Review Green Purchasing Checklist, located on the OSP website. Determine if applicable, complete and submit as required.
4 | Submit specifications to DHS to determine if a Hiring Agreement is applicable for the contract.
5 | Verify if there are Non-Visual Access requirements for the contract and update Section 4.33 in the RFP as needed.
6 | Consult with DBM for certification of Services contract procurements in accordance with the State Policy in State Personnel & Pension (SPP) §13-402 as defined in SPP §13-401.
7 | Obtain internal agency approvals. (Program, AAG, etc.)
8 | PROCUREMENT REVIEW PROCESS: STEP 1: Submit and Obtain approval of the SOLICITATION from DGS OSP for publication.
PROCURING (19 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
9 | IFB Publication: Advertise (post) the availability of the solicitation in eMaryland Marketplace Advantage (eMMA) and elsewhere. DIRECT SOLICIT: Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues. (Milestone Tracker Clock starts.)
ENTER eMMA Solicitation # HERE:
10 | Hold a Pre-Bid Conference.
11 | Prepare and distribute Minutes or a Summary of the conference to all known potential bidders and post in eMMA.
12 | Receive and consider solicitation questions; distribute answers to questions to all known potential bidders and post in eMMA.
13 | Prepare an addendum for any changes to the solicitation; distribute to all known potential bidders and post in eMMA.
14 | Bid Due Date: The Procurement Officer receives bids.
15 | Bids are opened publicly and a record is prepared of the bid opening (a bid abstract).
16 | Low bid is checked for compliance.
17 | Decide whether any deficiency in the low bid is waivable, curable, or renders the bid nonresponsive. Confirm low bidder is a responsible bidder. (Consult your AAG and write a Procurement Officer's Determination, if necessary.)
18 | Bidder is notified of any curable deficiencies.
19 | Bidder provides other required additional information or documents.
20 | PROCUREMENT REVIEW PROCESS: STEP 2: Submit and Obtain approval of the DRAFT AWARD DETERMINATION from DGS OSP for Agency Approval of the recommended awardee(s).
PROCURING (19 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
21 | Award Recommendation Date: The final award recommendation is made. The apparent awardee is informed and appropriate contract documents, affidavits, etc are sent for signature.
22 | If waiver request made, agency requests and considers MBE waiver documentation from recommended awardee, required additional MBE forms are obtained, if necessary, and the contractor signs the contract and affidavits; sends them to the Procurement Officer. USE CURRENT VERSIONS OF CONTRACT & AFFIDAVITS.
23 | Final internal agency approvals are obtained.
24 | PROCUREMENT REVIEW PROCESS: STEP 3: Submit and Obtain approval of the CONTRACT AWARD RECOMMENDATION from DGS OSP for final contract award.
24 | Contract Approval / BPW Date: The contract award is approved by DGS OSP and reported on the PAAR or submitted on a DGS OPS BPW Agenda for BPW approval, if required.
25 | The contract is signed by the agency and transmitted to the Contractor.
26 | Make sure the procurement file is completed, including a set of ALL bids received. (See COMAR 21.05.01.06-.07 for Procurement file requirements.)
27 | Post contract award on eMMA within 30 days of contract execution after all approvals have been finalized.
ENTER FMIS ADPICS # HERE:
ENTER eMMA Contract Award Posting # HERE:
PERFORMING (2 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
28 | Work initiation conference is held. (Kick-off Meeting and Notice-to-Proceed Letter)
29 | Contract Commencement Date: Contractor commences work.
I confirm that the above steps were completed for this Procurement.
| Procurement Officer Signature |  | Date
| Supervisor Signature |  | Date
Version 5, Dated 9/1/2026

## CSP CHECKLIST
(Agency) PROCUREMENT PROCESS PLAN FOR (Contract Title)
44 STEPS / CHECKLIST & TIMELINE FOR COMPETITIVE SEALED PROPOSALS (CSP) PROCUREMENTS
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK)
PLANNING (9 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
1 | Initial Planning Meeting: Identify what you want to procure.
> BPO Number of current contract (final option)
> Expiration Date of current contract (final option)
> Procurement Method
2 | Specification Drafting: Prepare specifications and determine the means for advertising and distributing the solicitation. Develop a direct solicitation list. Hold PRG, determine SBR designation, set MBE and VSBE goals and MBE subgoals, as appropriate. Work with AAG as needed. USE CURRENT RFP TEMPLATE.
3 | Review Green Purchasing Checklist, located on the OSP website. Determine if applicable, complete and submit as required.
4 | Submit specifications to DHS to determine if a Hiring Agreement is applicable for the contract.
5 | Verify if there are Non-Visual Access requirements for the contract and update Section 4.33 in the RFP as needed.
6 | Consult with DBM for certification of Services contract procurements in accordance with the State Policy in State Personnel & Pension (SPP) §13-402 as defined in SPP §13-401.
7 | Confirm members for the Evaluation Committee.
8 | Obtain internal agency approvals. (Program, AAG, etc.)
9 | PROCUREMENT REVIEW PROCESS: STEP 1: Submit and Obtain approval of the SOLICITATION from DGS OSP for publication.
PROCURING (33 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
10 | RFP Publication: Advertise (post) the availability of the solicitation in eMaryland MarketPlace and elsewhere. DIRECT SOLICIT: Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues. (Milestone Tracker Clock starts.)
ENTER eMMA Solicitation # HERE:
11 | Hold a Pre-Proposal Conference.
12 | Prepare and distribute Minutes or a Summary of the conference to all known potential offerors and post in eMMA.
13 | Receive and consider solicitation questions; distribute answers to questions to all known potential offerors and post in eMMA.
14 | Prepare an addendum for any changes to the solicitation; distribute to all known potential offerors and post in eMMA.
15 | Proposal Due Date: The Procurement Officer receives proposals.
16 | Technical proposals are opened in the presence of at least 2 State employees, not publicly, a record is prepared of the proposals received (a register of proposals) and of the opening. Check for separate technical and financial proposals, bond or other required security. Do not open financial proposals.
17 | Evaluation Period Begins: Technical Proposals are checked for compliance with various requirements, checking first the completion of MBE forms. (Any MBE deficiencies should be confirmed with AAG to see if curable, waivable, or fatal.)
PROCURING (33 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
18 | Evaluation Kick-off Meeting: The Procurement Officer reviews the "Evaluation Committee Responsibilities and Duties" with the evaluation committee, provides them a copy of the guidelines and has them sign the confidentiality and commitment portion of the document, then distributes the technical proposals to each member to individually read.
19 | The evaluation committee meets to discuss the technical proposals, including strengths and weaknesses, ambiguities, and omissions.
20 | “Cure letters” are issued to Offerors to address:
> Omitted items or information and exceptions
> Written clarifications of ambiguous material
> Written explanations or justifications for any information that is not sufficiently supported
21 | Cure letter responses are received and reviewed.
22 | The evaluation committee prepares generic and specific questions to ask offerors at the oral presentations, including any lingering or new questions based upon the cure letter responses.
23 | Oral presentations are held with all offerors.
24 | Offerors submit additional information, clarifications or changes based upon the oral presentations.
25 | If any Offeror is determined to be not technically qualified or not reasonably susceptible of being selected for award, a Procurement Officer's Determination must be written and the Offeror must be rejected, prior to opening of Financial proposals through a formal rejection letter.
26 | Final Technical Evaluation Meeting: The evaluation committee makes final technically qualified determinations for proposals and ranks the remaining technically qualified proposals based upon the evaluation criteria in the RFP, including proposals, cures & orals.
27 | Opening of Financial Proposals: Open and review financials for offerors with technically qualified proposals.
28 | If necessary, discussions are held concerning the financial proposals with ALL Offerors still being considered.
29 | Best and Final Offers (BAFO) are invited, received and evaluated.
30 | Final Financial and Overall Ranking Meeting: Based upon the combined technical and financial rankings the evaluation committee recommends an offeror to receive the contract award.
31 | PROCUREMENT REVIEW PROCESS: STEP 2: Submit and Obtain approval of the DRAFT AWARD DETERMINATION from DGS OSP for Agency Approval of the recommended awardee(s).
32 | Award Recommendation Date: The procurement officer and agency head accept the recommendation of the evaluation committee or *select a different offeror for the award.
33 | The apparent awardee is informed and appropriate contract documents, affidavits, etc are sent for signature.
34 | USE CURRENT VERSIONS OF CONTRACT & AFFIDAVITS. The contractor signs the contract and provides all required post award items, such as:
> 2 additional MBE forms, or waiver justification
> Bonds
> Insurance
> Contract and Conflict-of-Interest Affidavits
PROCURING (33 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
35 | Non-winning offerors are notified of their status and provided all permissible information
36 | Debriefings are scheduled and held.
37 | Final internal agency approvals are obtained.
38 | PROCUREMENT REVIEW PROCESS: STEP 3: Submit and Obtain approval of the CONTRACT AWARD RECOMMENDATION from DGS OSP for final contract award.
39 | Contract Approval / BPW Date: The contract award is approved by DGS OSP and reported on the PAAR or submitted on a DGS OPS BPW Agenda for BPW approval, if required.
40 | The contract is signed by the agency and transmitted to the Contractor.
41 | Make sure the procurement file is completed. Excess copies of proposals are destroyed and the procurement file is completed. (One full set of all Offerors' proposals - technical, financial & BAFO - must be maintained in the file. See COMAR 21.05.01.06-.07 for Procurement file requirements.)
42 | Post contract award on eMMA within 30 days of contract execution after all approvals have been finalized.
ENTER FMIS ADPICS # HERE:
ENTER eMMA Contract Award Posting # HERE:
PERFORMING (2 steps)
| STEP | START DATE | TARGET COMPLETION DATE | ACTUAL COMPLETION DATE
43 | Work initiation conference is held. (Kick-off Meeting and Notice-to-Proceed Letter)
44 | Contract Commencement Date: Contractor commences work.
I confirm that the above steps were completed for this Procurement.
| Procurement Officer Signature |  | Date
| Supervisor Signature |  | Date
Version 5, Dated 9/1/2026

## PROCUREMENT REVIEW DOCS
DGS OSP PROCUREMENT REVIEW PROCESS STEPS & REQUIRED DOCUMENTATION TO BE SUBMITTED FOR APPROVALS
The following documents MUST be included in the Procurement Review Process Step Submission Packages in order to be considered "A Complete Full Submission Package" for DGS OSP review and approval. Any missing documentation will cause the submission package to be rejected back to the agency procurement officer. Only complete submission packages will be reviewed. If your package is rejected, your resubmission MUST include all required documentation for the specific STEP being reviewed.
PROCUREMENT REVIEW PROCESS: STEP 1: Submit and Obtain approval of the SOLICITATION from DGS OSP for publication.
Draft solicitation, including all edited supplementals, appendices, exhibits, and attachments.
Legal sufficiency from the AAG for the solicitation.
Any other agency certifications, waivers, exemptions approved from the checklist - Living Wage, Hiring Agreement, State Personnel and Pension (SPP) Services Policy, etc.
Follow DGS OSP/BPW Approval Checklist as noted below for this Step 1:
DBM certification memo for SPP §13-402 for Services Contracts (if applicable)
Preferred Provider Waivers: MCE, BISM, or MD Works Waiver (If applicable)
Fund Certification (Fund Source, including Source of Special Funds)
Statement of Work (SOW) (In the Solicitation)
Procurement Review Group (PRG) Documentation - SBR designation; MBE participation goals; MBE subgoals; VSBE participation goals
Small Business Reserve (SBR) Waiver (Proof of email request to GOSBA+72 hour response time)
If no SBR, Small Business Preference for IFBs.
PROCUREMENT REVIEW PROCESS: STEP 2: Submit and Obtain approval of the DRAFT AWARD DETERMINATION from DGS OSP for Agency Approval of the recommended awardee(s).
Draft Award Recommendation Letter with POD for awardee(s). (Unsigned.)
For RFPs, it should describe the full evaluation process and how the evaluation committee came to a consensus on the award or if the Procurement Officer went against the Evaluation Committee.
Screenshot of the "Analyze and Award Tab" in eMMA
eMMA BPM # - for public solicitation review to see all amendments and that the solicitation was posted the correct number of days
Evaluation Committee signoff on the Final Ranking document for RFPs.
List of Technical Evaluation Strengths and Weaknesses for RFPs.
Copies of the Letters to Bidders/Offerors determined to be not responsible or the bids not responsive or proposals not reasonably susceptible of being selected for award.
Follow DGS OSP/BPW Approval Checklist as noted below for this Step 2:
MBE/DBE/VSBE D-1 and E-1 (Forms D/E) (all that apply)
MBE/DBE/VSBE Waiver (all that apply)
If Protest Received (Provide documentation to include: protest + agency response + MSBCA documents, if applicable)
DRAFT - Procurement Officer's Award Recommendation (POD)
State Department of Assessments and Taxation (SDAT) Evidence of Good Standing (SDAT Website or VGSC App)*
MD Tax Clearance Number (obtained from Comptroller of Maryland’s Office)
Verification of Debarment Status (BPW Debarment List, SAM.gov , or EECA App)
eMaryland Marketplace Advantage (eMMA) Solicitation Advertisement (BPM No.)
List of ALL Directly Solicited Bidders/Offerors beyond vendors solicitated in eMMA, or indicate if no direct solicitation.
Copies of All Responsive Bids or Reasonably Susceptible Proposals (Financial Offers only)
Statement of Work (SOW) (In the Solicitation)
Bid/Proposal Affidavit
DHS Hiring Agreement (If Applicable)
Living Wage Affidavit (For Facilities/Maintenance (FM/M) & Professional Services (S) Contracts over $100K)
PROCUREMENT REVIEW PROCESS: STEP 3: Submit and Obtain approval of the CONTRACT AWARD RECOMMENDATION from DGS OSP for final contract award.
Agency Head Signed Award Recomendation
Vendor Signed Contract
Legal Sufficiency from the AAG for the contract.
FMIS Crosswalk (In ADPICS Notepad) - ADPICS # and BPM #
Timing from Debriefings for protests has passed - provide dates of debriefings and debriefing documents for each offeror
Copies of the Letters to the Non-Select Bidders/Offerors
Follow DGS OSP/BPW Approval Checklist as noted below for this Step 3:
BPW Action Agenda Item in appropriate template (Submitted in Microsoft WORD)
If Seeking Retroactive Approval - Request to Ratify Void/Voidable Contract (Provide Retro Action Letter MUST BE signed by Secretary/Agency Head)
DGS OSP is required to make an initial determination of void or voidable for the contract action and add appropriate language to the Action Agenda Item.
MBE/DBE/VSBE Participation Schedule (Forms D/E) (all that apply) (FORMS MUST MATCH AGENDA ITEM)
If Protest Received (Provide documentation to include: protest + agency response + MSBCA documents, if applicable)
Agency head determination of substantial State interest if seeking BPW approval in the face of protest or MSBCA Appeal
FINAL/SIGNED - Procurement Officer's Award Recommendation (POD) approved by the Agency Head or Designee.
Fund Certification (Fund Source, including Source of Special Funds)
State Department of Assessments and Taxation (SDAT) Evidence of Good Standing (SDAT Website or VGSC App)
MD Tax Clearance Number (obtained from Comptroller of Maryland’s Office)
Verification of Debarment Status (BPW Debarment List, SAM.gov , or EECA App)
FMIS Crosswalk Screenshots (2342-Approval Path, 9100-Notepad, 2345-MBE Screens) or eMaryland Marketplace Advantage (eMMA) CTR # Workflow, Header and Additional Information Screens
Contract (w/vendor signature, AAG signature/memo for Legal Sufficiency and all applicable Affidavits, bonds, and insurance certificates)
Statement of Work (SOW) (If no contract included, otherwise, should be referenced as part of the contract)
Contract Affidavit
Corporate Diversity Addendum (If Applicable) (Form & Affidavit)